# Free Launch Plan Checklist

Releasing a Movie, Album, or Show? Map Out Pre-Launch Buzz, Influencer Collabs & PR Content

## 1. How to Use This Checklist

- Copy the sections and tables into your project management tool or spreadsheet.

- Assign each action to an owner with clear deadlines.

- Track status and key metrics to ensure momentum.

- Review weekly and adjust based on results.

## 2. Strategy & Goals

| # | Objective | KPI / Target | Owner | Deadline |
| --- | --- | --- | --- | --- |
| 1 | Build awareness pre-launch | 100K impressions across channels | Marketing | D–30 |
| 2 | Drive trailer / single listens | 50K trailer views or 20K streams | Digital Ops | D–25 |
| 3 | Secure media coverage | 10 articles / features | PR Lead | D–20 |
| 4 | Activate influencers | 5 key influencer takeovers | Social Lead | D–15 |
| 5 | Pre-sales / pre-saves | 5K pre-bookings or pre-saves | Sales Lead | D–10 |

## 3. Pre-Launch Activities

| # | Action | Description | Owner | Timeline | Status |
| --- | --- | --- | --- | --- | --- |
| 6 | Finalize branding & key visuals | Posters, banners, cover art, thumbnail designs | Creative | D–40 | ☐ |
| 7 | Launch teaser trailer / snippet | 15–30s teaser across social channels | Video Team | D–30 | ☐ |
| 8 | Set up pre-order / pre-save page | Website, Spotify, iTunes, ticketing platform | Ops | D–28 | ☐ |
| 9 | Email sequence: teaser → reveal → reminder | 3-email drip to mailing list | CRM Lead | D–25 / D–18 / D–10 | ☐ |
| 10 | Countdown widget on website & socials | Daily countdown posts/stories | Social | D–14 to D | ☐ |

## 4. Influencer & PR Collabs

| # | Action | Partner Type | Deliverable | Owner | Timeline | Status |
| --- | --- | --- | --- | --- | --- | --- |
| 11 | Identify & brief top 5 influencers | Micro, Macro, Celebrity | Story/Reel scripts & assets | Social | D–30 | ☐ |
| 12 | Send media kits & press release | Entertainment, Lifestyle | Press release + imagery bundle | PR Lead | D–28 | ☐ |
| 13 | Secure interviews & features | Podcasts, Blogs | Booking confirmations | PR Lead | D–20 | ☐ |
| 14 | Arrange influencer watch-listen party | Virtual or in-person | Invite list + event plan | Events | D–15 | ☐ |
| 15 | Collaborate on UGC #Hashtag campaign | Fans + influencers | UGC guidelines & hashtag strategy | Social | D–10 to D | ☐ |

## 5. Marketing & Advertising

| # | Action | Channel / Tool | Budget (₹) / Notes | Owner | Timeline | Status |
| --- | --- | --- | --- | --- | --- | --- |
| 16 | Run paid social ads (teaser & trailer) | FB/IG, YouTube | 🎯 Target lookalikes & enthusiasts | Paid Ads | D–25 to D | ☐ |
| 17 | Google Search & Display campaigns | Google Ads | Keywords: title, cast, genre, lyrics | Paid Ads | D–20 to D | ☐ |
| 18 | Retarget website visitors | FB Pixel, Google Tag | Carousel of scenes, snippets | Paid Ads | D–15 to D | ☐ |
| 19 | Audio ads on Spotify / podcast sponsorships | Spotify, Anchor Ads | 30s audio spot | Marketing | D–20 to D | ☐ |
| 20 | PR spotlight ads in industry newsletters | Trade publications | Native ad placement | PR Lead | D–30 | ☐ |

## 6. Launch Day Execution

| # | Action | Description | Owner | Day-Of Time | Status |
| --- | --- | --- | --- | --- | --- |
| 21 | Host live premiere / listening party | Instagram Live, YouTube Premiere | Creative | Launch Hour | ☐ |
| 22 | Amplify UGC: share fan reactions | Repost stories, tweets, TikToks | Social | Throughout Day | ☐ |
| 23 | Send launch announcement | Email blast + SMS reminder | CRM Lead | Launch +1 hr | ☐ |
| 24 | Monitor & respond to feedback | Dedicated hashtag tracking & moderation | Community Mgr | D to D+2 | ☐ |
| 25 | Publish “making-of” or behind-the-scenes | Blog post or YouTube short | Content | D+1 | ☐ |

## 7. Post-Launch Sustaining Momentum

| # | Action | Description | Owner | Timeline | Status |
| --- | --- | --- | --- | --- | --- |
| 26 | Share performance recap & thank-you video | Short edit with highlights & metrics | Video Team | D+3 | ☐ |
| 27 | Publish fan testimonials & reviews | Carousel or video montage | Social | D+5 | ☐ |
| 28 | Offer limited-time merch or bonus track | Email/Social promotion | Marketing | D+7 to D+14 | ☐ |
| 29 | Analyze funnel metrics & identify gaps | Review impressions → streams/views → sales | Analytics | D+10 | ☐ |
| 30 | Plan follow-up content (remix, live Q&A) | Interactive session or bonus snippet release | Creative | D+14 to D+30 | ☐ |

## 8. Credits & Next Steps

Crafted by the entertainment marketing experts at Marketing Mojito, your partner for buzzworthy launches.

- Download editable checklist template: https://marketingmojito.com/free-resources

- Campaign Strategy & Execution Services: https://marketingmojito.com/services/campaign-marketing

- Book a Launch Planning Session: https://marketingmojito.com/book-consultation

Next: Fill in this plan with your project details, align your team, and get ready to launch with maximum impact!

🌐Website: www.marketingmojito.com

📧Email: hello@marketingmojito.com

📸Instagram: @marketingmojitoindia

🔗Linkedin:  www.linkedin.com/company/marketing-mojito

📘Facebook: www.facebook.com/marketingmojito