# Free Product Launch Checklist for D2C Brands

Ready to Go Live? Every Pre-Launch Detail Covered—from Samples to Creatives

## 1. How to Use This Checklist

- Copy into your favorite project management tool or spreadsheet.

- Assign each task to an owner with clear deadlines.

- Track status and metrics as you move through each phase.

- Review daily during the final two weeks before launch.

## 2. Pre-Launch (8–6 Weeks Out)

| # | Task | Owner | Due Date | Status |
| --- | --- | --- | --- | --- |
| 1 | Finalize product formula & packaging design | Product Team | D–56 | ☐ |
| 2 | Order & QA product samples for photography & testing | Operations | D–54 | ☐ |
| 3 | Conduct consumer focus group / feedback sessions | Insights | D–50 | ☐ |
| 4 | Lock in pricing, SKU variants, and inventory levels | Finance | D–48 | ☐ |
| 5 | Develop brand messaging & USP statements | Marketing | D–46 | ☐ |
| 6 | Brief creative team on visual style guide | Creative | D–44 | ☐ |
| 7 | Shoot product imagery & lifestyle photos | Creative | D–42 | ☐ |
| 8 | Produce hero launch video (15–30s) | Video Team | D–40 | ☐ |
| 9 | Build & QA launch landing page + checkout flow | Web Dev | D–38 | ☐ |
| 10 | Set up analytics & conversion tracking | Analytics | D–36 | ☐ |

## 3. Launch Preparation (5–2 Weeks Out)

| # | Task | Owner | Due Date | Status |
| --- | --- | --- | --- | --- |
| 11 | Draft email sequence (teaser → launch → follow-up) | CRM Manager | D–35 | ☐ |
| 12 | Plan social media calendar & influencer outreach | Social Lead | D–33 | ☐ |
| 13 | Create paid ad campaigns (social, search, display) | Paid Ads | D–32 | ☐ |
| 14 | Prepare PR assets & press release | PR Lead | D–30 | ☐ |
| 15 | Line up affiliate partners & promo codes | Partnerships | D–28 | ☐ |
| 16 | Schedule live-streamed launch event or webinar | Events | D–26 | ☐ |
| 17 | QA test checkout, discount codes, and shipping rules | QA / Ops | D–24 | ☐ |
| 18 | Upload all assets (images, video, copy) to CMS | Content Ops | D–22 | ☐ |

## 4. Launch Week (1 Week Out to Launch Day)

| # | Task | Owner | Due Date | Status |
| --- | --- | --- | --- | --- |
| 19 | Send “1 Week to Go” countdown email | CRM Manager | D–7 | ☐ |
| 20 | Teaser social countdown posts & Stories | Social Lead | D–7 to D–1 | ☐ |
| 21 | Final PR pitch reminders to media | PR Lead | D–5 | ☐ |
| 22 | Influencer seeding & unboxing videos | Influencer Mgr | D–3 | ☐ |
| 23 | Final site load & performance test | Web Dev | D–2 | ☐ |
| 24 | Prepare customer support scripts & FAQs | Support Lead | D–1 | ☐ |
| 25 | Go-live launch email + social announcement | Marketing | D-Day | ☐ |
| 26 | Host live event / webinar | Events | D-Day | ☐ |
| 27 | Monitor site performance & ad spend in real time | Analytics / Paid Ads | D-Day | ☐ |

## 5. Post-Launch (1–4 Weeks After)

| # | Task | Owner | Due Date | Status |
| --- | --- | --- | --- | --- |
| 28 | Send “Thank You” email + feedback survey | CRM Manager | D+1 | ☐ |
| 29 | Analyze launch metrics (traffic, conversion, revenue) | Analytics | D+3 | ☐ |
| 30 | Share UGC & initial reviews on social | Social Lead | D+5 | ☐ |
| 31 | Optimize ad campaigns based on performance | Paid Ads | D+7 | ☐ |
| 32 | Run retargeting campaigns to cart abandoners | Paid Ads | D+10 | ☐ |
| 33 | Host “Ask Me Anything” with founder or designer | Social / Events | D+14 | ☐ |
| 34 | Refresh landing page messaging & creative tests | Creative / Web Dev | D+21 | ☐ |
| 35 | Plan follow-up upsell / cross-sell emails | CRM Manager | D+28 | ☐ |

## 6. Credits & Next Steps

Crafted by the e-commerce growth experts at Marketing Mojito, helping D2C brands launch with confidence.

- Download the editable checklist template: https://marketingmojito.com/free-resources

- D2C Launch Strategy & Execution Services: https://marketingmojito.com/services/digital-marketing

- Book your Launch Planning Session: https://marketingmojito.com/book-consultation

🌐Website: www.marketingmojito.com

📧Email: hello@marketingmojito.com

📸Instagram: @marketingmojitoindia

🔗Linkedin:  www.linkedin.com/company/marketing-mojito

📘Facebook: www.facebook.com/marketingmojito

Next: Populate this checklist with your dates and details, align your teams, and execute a seamless, high-impact product launch!